## Sheet1 (hidden)
Minutes of Meeting
Meeting Title: | Angola Process Demo
Date: | 2025-01-20
Time: | 3PM
Location: | Virtual+Offline
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Syed Sir
Kishor N.
Hasim
Pooja Bagul
AjayKumar
Nikhita M.
Agenda Items:
[Agenda Item 1]
| Discussion: | 1. Demo Presentation: A demonstration was shown. 2. Additional Point: We need to verify whether the price change is low or high. 3.Deadline: The task must be completed by February 1st, 2025. 4.Document Request: Please share the required documentation for future development, UAT, and go-live. These documents are mandatory for moving forward.
| Decisions Made: | 1. Any changes discussed regarding the price adjustments in the inventory will be reflected once the process goes live
Action Items:
| Responsible person | Reinaldo
Next Steps: | UAT with real data can only be conducted once the required documents are provided.
Next Meeting:
Date: | 2025-01-27
Time: | 1PM UAE Timing
Location/Platform: | Teams Meeting

## Sheet2 (hidden)
Minutes of Meeting
Meeting Title: | Angola Process Demo
Date: | 2025-02-18
Time: | 3PM IST
Location: | Virtual+Offline
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Rajesh S
Hasim
Pooja Bagul
Nikhita M.
Reinaldo
Hamid
Andre
Agenda Items:
[Agenda Item 1]
| Discussion: | 1. if COT file is having multiple pages more than 2 or 3pages. (once only we are opening the ERP for multiple files) 2. End user have to choose best COT 3.*Invoice generation monthly (2nd part, we did not discuss priorly) 4.*As of now we do not have any validation on item price. (suggestion is to do separately; for 1 COT- 2payment invoice) end user need notification if we any intervention is required. 5.Put COT file as it is, no need to change filename.
| Decisions Made: | 1.By Friday i.e., we will give best solution can be done
Action Items:
| Responsible person | Pooja B.
Next Steps: | UAT with real data can only be conducted once the required documents are provided.
Next Meeting:
Date: | 2025-02-21
Time: | 3PM IST Timing
Location/Platform: | Teams Meeting

## 24-02-25
Minutes of Meeting
Meeting Title: | ERP Process Queries Resolution by Saisoft Team - Meeting Agenda
Date: | 2025-02-24
Time: | 3PM IST
Location: | Virtual
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Rajesh S
Hasim
Pooja Bagul
Nikhita M.
Reinaldo
Hamid
Andre
Agenda Items:
| [Agenda] | ERP Process Queries Resolution by Saisoft Team - Meeting Agenda
| Discussion: | 1. PO Closure on ERP system walkthrough Meeting : i.) Scheduled for tomorrow at 1:30 PM IST. 2. ERP Process Testing : i.) The Angola team will begin testing the ERP process from 25th Feb 2025, which was deployed on 1st Feb on the Angola system. 3. ERP Process Testing Feedback Discussion : i.) Planned for Friday. 4. Knowledge Transfer & Test Cases for ERP Process : i.) The Saisoft team will share KT materials and test cases. 5. COT Item Price Check : i.) In partial payments, price changes occur due to currency fluctuations; the updated price should be taken from the National Bank of Angola portal. ii.) The Angola team will propose an improved approach for managing price changes.
| Decisions Made: | 1. PO Closure walkthrough meeting on the ERP system – Scheduled for Wednesday (26-02-2025). 2. Discussion on process testing feedback – Scheduled for Friday (28-02-2025).
| Action Items: | 1. The client team will test the ERP process and provide feedback by Friday (28-02-2024).
| Responsible person | Reinaldo.
Next Steps: | PO Closing Meeting – ERP System Discussion on 25th Feb 2025
Next Meeting: | 2025-02-26
Date: | 2025-02-26
Time: | 2:30 PM IST Timing
Location/Platform: | Teams Meeting

## 27-02-25
Minutes of Meeting
Meeting Title: | ERP Process Testing and Discussion
Date: | 2025-02-27
Time: | 2:30 PM IST
Location: | Virtual
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Rajesh S
Kishor N
Hasim
Pooja Bagul
Nikhita M.
Reinaldo
Hamid
Andre
Agenda Items:
| [Agenda] | ERP Process Testing feedback Meeting Agenda
| Discussion: | 1. ERP Testing Remarks: a) While generating a PO on ERP, the Watt value (14) should not be included. b) VFA is mandatory for completing ERP process testing and proceeding to go live. c) The VFA component will be developed, and we will update the Angola team after receiving the required documents. d) The Angola team does not want voucher file involvement in the process. 2. GRN Process: After closing the current ERP process, we will proceed with the GRN process.
| Decisions Made: | 1.We will develop the VFA component within the ERP process. 2.To proceed, we require a sample email and invoice file from the Angola team for the remaining development. 3. A meeting is scheduled with the Angola team on February 28, 2025, to discuss handling different types of invoices received from suppliers.
| Action Items: | To proceed with the VFA development, we require a sample email and invoice file from the Angola team. Kindly share these documents at the earliest to complete the remaining development.
| Responsible person | Reinaldo.
Next Steps: | 1. We are currently working on VFA generation 2. The Saisoft team will provide a solution for handling multiple invoice formats.
Next Meeting: | 2025-02-28
Date: | 2025-02-28
Time: | 2:30 PM IST Timing
Location/Platform: | Teams Meeting

## 12-03-2025
Minutes of Meeting
Meeting Title: | ERP Process Testing and Discussion
Date: | 2025-03-13
Time: | 12:30 PM IST
Location: | Virtual+Offline
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Syed Sir
Rajesh S
Pooja Bagul
Nikhita M.
Agenda Items:
| [Agenda] | Demo- ERP Application
| Discussion: | ERP Testing Remarks: 1. Multiple COT documents. 2. Folder Name renaming. 3. Inventory item balancing. 4. GRN (Depended on User end, user have to provide us GRN) 5. Payment letter (We need to check feasibility about selecting bank invoice)
| Decisions Made: | #Changes suggested-: 1. Multiple COT documents. 2. Folder Name renaming. 3. Inventory item balancing while generating PO. 4. GRN (Depended on User end, user have to provide us GRN) 5. Payment letter (We need to check feasibility about selecting bank invoice)
| Action Items: | Working on changes suggested. But these changes are made as final change, afterwards we will not accept the changes.
| Responsible person | Saisoft Team
Next Steps: | Come up the development of suggested chnages by next week.
Next Meeting: | -
Date: | -
Time: | -
Location/Platform: | -

## 20-03-2025
Minutes of Meeting
Meeting Title: | ERP Process Testing and Discussion
Date: | 2025-03-20
Time: | 12:30 PM UAE
Location: | Virtual+Offline
Meeting Facilitator: | Pooja Bagul
Note Taker: | Pooja Bagul
Attendees: | Kishor N
Rajesh S
Pooja Bagul
Nikhita M
Syed Sir
Levis
Reinalod
Agenda Items:
| [Agenda] | Final Demo of ERP Process Automation.
| Discussion: | 1. Process Demo was successful. 2. Queries and solutions :- 1. Exchange Rate (Handled via ERP) 2. Final Invoice (Handled via ERP) 3. Good service (Handled via ERP) 4. Tax calculation (Handled via ERP) 5. Select COT best price (End-User have to choose and place into respective folder) 6. Inventory Stock Availbility (Handled via ERP) 7. Payment Letter generation partial or full (Based on vendor's email invoice attached)
| Decisions Made: | 1. From 20-3-2025 to 31-3-2025 UAT of the process 2. On 1st April 2025 we will make ERP Process live 3. Reinaldo has to share us required data of sample email with invoice attached. 4. Reinaldo has to update the inventory on ERP
| Action Items: | 1. Reinaldo has to share us required data of sample email with invoice attached. 2. Reinaldo has to update the inventory on ERP
| Responsible person | Reinaldo
Next Steps: | 1. From 20-3-2025 to 31-3-2025 UAT of the process 2. On 1st April 2025 we will make ERP Process live. 3. Reinaldo has to share us required data of sample email with invoice attached. 4. Reinaldo has to update the inventory on ERP
Next Meeting:
Date: | -
Time: | -
Location/Platform: | -